## 2022-23
Effort Estimation for PLFS ETL & Testing (Through Database Queries) for 1 Year
S. No. | Sheet Category in PLFS Spreadsheet | Number of Data Blocks | Row Start | Row End | Column Start | Column Until | Total Number of Indices | Status | Count & Last-End Value Matching | BA Testing | Remarks
1 | Table No.6 | 4 | 7 | 43 | B | J | 1332 | Done | Yes | Pending
2 | Table No. 7 | 4 | 7 | 43 | B | J | 1332 | Done | Yes | Pending
3 | Table No. 8 | 4 | 7 | 43 | B | J | 1332 | Done | Yes | Pending
4 | Table No. 11 | 9 | 9 | 45 | B | K | 3330 | Done | Yes | Pending
5 | Table No. 12 | 9 | 9 | 45 | B | K | 3330 | Done | Yes | Pending
6 | Table No. 13 | 9 | 9 | 45 | B | K | 3330 | Done | Yes | Pending
7 | Table No. 17 | 2 | 7 | 43 | B | J | 666 | Done | Yes | Pending
8 | Table No. 18 | 2 | 7 | 43 | B | J | 666 | Done | Yes | Pending
9 | Table No. 19 | 2 | 7 | 43 | B | J | 666 | Done | Yes | Pending
10 | Table No. 4 | 9 | 8 | 44 | B | K | 3330 | Done | Yes | Pending
11 | Table No. 9 | 9 | 9 | 45 | B | G | 1998 | Done | Yes | Pending
12 | Table No. 10 | 9 | [7 empty] | Pending
13 | Table No. 14 | 1 | [7 empty] | Pending
14 | Table No. 15 | 1 | [7 empty] | Pending
15 | Table No. 16 | 9 | 8 | 44 | B | U | 6660 | Done |  | Pending
16 | Table No. 20 | 3 | 8 | 44 | B | M | 1332 | Done |  | Pending
17 | Table No. 21 | 9 | 9 | 45 | B | G | 1998 | Done |  | Pending
18 | Table No. 22 | 9 | 9 | 45 | B | J | 2997 | Done |  | Pending
19 | Table No. 23 | 3 | 9 | 45 | B | J | 999 | Done |  | Pending
20 | Table No. 24 | 4 | 7 | 43 | B | J | 1332 | Done |  | Pending
21 | Table No. 25 | 4 | 7 | 43 | B | J | 1332 | Done |  | Pending
22 | Table No. 26 | 4 | 7 | 43 | B | J | 1332 | Done |  | Pending
23 | Table No. 27 | 36 | 10 | 46 | B | S | 23976 | Done |  | Pending
24 | Table No. 28 | 36 | 10 | 10 | B | G | 216 | Done |  | Pending
25 | Table No. 33 | 9 | 9 | 9 | B | J | 81 | Done |  | Pending
26 | Table No. 34 | 9 | 9 | 9 | B | W | 198 | Done |  | Pending
27 | Table No. 35 | 36 | 10 | 46 | B | I | 10656 | Done |  | Pending
28 | Table No. 36 | 36 | 10 | 46 | B | I | 10656 | Done |  | Pending
[6 empty] | SUM | 85077
[6 empty] | Total No of Sheets |  |  | 281
[6 empty] | Unique Formats |  |  | 17

## 2021-22
S. No. | Sheet Category in PLFS Spreadsheet | Number of Data Blocks | Row Start | Row End | Column Start | Column Until | Total Number of Indices | Status | Count & Last-End Value Matching | BA Testing | Remarks
1 | Table No. 8 | [6 empty] | Done
2 | Table No.16.0 | [6 empty] | Done
3 | Table No. 17.0 | [6 empty] | Done
4 | Table No. 18.0 | [6 empty] | Done
5 | TableNo. 19 | [6 empty] | Done
6 | Table No. 20.0 | [6 empty] | Done
7 | Table No. 22.0 | [6 empty] | Done
8 | Table No. 23.0 | [6 empty] | Done
9 | Table No. 24.0 | [6 empty] | Done
10 | Table No.26.0 | [6 empty] | Done
11 | Table No. 27.0 | [6 empty] | Done
12 | Table No. 34.0 | [6 empty] | Done
13 | Table No. 35.0 | [6 empty] | Done
14 | Table No. 37.0 | [6 empty] | Done
15 | Table No. 38.0 | [6 empty] | Done
16 | Table No. 40.0 | [6 empty] | Done |  |  |  | State Error
17 | Table No. 41.0
18 | Table No. 42.0 | [6 empty] | Done
19 | Table No. 43.0 | [6 empty] | Done
20 | Table No. 44.0 | [6 empty] | Done
21 | Table No. 45.0 | [6 empty] | Done
22 | Table No. 36.0 | [6 empty] | Done
23 | Table No. 46.0 | [6 empty] | Done
24 | Table No. 47 | [6 empty] | Done |  |  |  | 2 Type 1 Done
25 | Table No. 57 | [6 empty] | Done
26 | Table No. 25.0 | [6 empty] | Done
27 | Table No.29.0 | [6 empty] | Done |  |  |  | Not all staete
28 | Table No.30.0
29 | Table No.31.0
Table No. 36.0
Table No. 46.0
Table No. 47
Table No. 57
Table No. 25.0
Table No.29.0
Table No.30.0
Table No.31.0